## Calgary recovery
Week | Week Starting | Parcels | On-Time Delivery % | Induction On-Time % | Missed Cut-Off Drops | Delivery Exceptions | Returns Rate % | Notes
W1 | 2026-03-16 | 3520 | 90.4 | 62 | 34 | 141 | 7.6 | Recovery starts. Baseline week.
W2 | 2026-03-23 | 3610 | 91.1 | 68.5 | 29 | 128 | 7.4
W3 | 2026-03-30 | 3480 | 92 | 74.2 | 24 | 112 | 7.1 | Revised cut-off communicated to customer.
W4 | 2026-04-06 | 3395 | 89.8 | 76 | 22 | 168 | 7.9 | Freezing rain 07-09 April, regional road closures.
W5 | 2026-04-13 | 3702 | 92.8 | 80.1 | 19 | 106 | 6.8
W6 | 2026-04-20 | 3758 | 93.6 | 84.6 | 15 | 94 | 6.5
W7 | 2026-04-27 | 3690 | 94.2 | 87.3 | 12 | 85 | 6.2 | Findings issued to customer 30 April.
W8 | 2026-05-04 | 3811 | 94.6 | 89 | 10 | 78 | 6

## Read me
Calgary service recovery — weekly tracking
Period | Week 1 begins 2026-03-16. Recovery runs ninety days.
Requirement | 95% on-time. The customer's own supplier scorecard.
FY2025 baseline | Calgary averaged 90.2% on-time, the lowest site in the network in all twelve months.
Induction On-Time % | Share of customer drops arriving before the Calgary sortation cut-off. Measured at the dock.
Missed Cut-Off Drops | Count of drops after the cut-off. A subset of the above, kept separately because it is what the customer can act on.
Delivery Exceptions | Any parcel that did not complete its planned route on the planned day, for any reason.
What this workbook establishes | That on-time delivery has improved since the recovery began, and that induction compliance improved alongside it.
What it does not establish | That induction timing is the only cause. Week 4 shows on-time falling while compliance rose. Weather is recorded, not proven.